## Sheet1
Group 6 | Dylan Corless, Bora Girbay, Douglas Martiniuk, Kevin Ranaweera, Jawan Toor, Karen Joy Tragura
WBS ID | Task Name | Owner | Duration (Days) | Notes
0.0 | NAIT End of Term LAN Party | Group 6 | 48 days
1.0 | Research LAN Party | Jawan | 5 days
1.1 | Research equipment needed | Jawan | 1 day
1.1.1 | Research network and power requirements for equipment | Jawan | 1 day
1.1.2 | Research peripherals required | Jawan | 1 day
1.2 | Research how to book room at NAIT | Karen | 3 days
1.2.1 | Inquire about capacity limits | Karen | 3 days
1.2.2 | Inquire about equipment that can be provided by NAIT | Karen | 3 days
1.3 | Research possible sponsors | Bora | 1 day
1.3.1 | Create a sponsor pitch deck | Bora | 1 day
1.4 | Research possible vendors | Kevin | 1 day
1.5 | Research games that will be played | Dylan | 1 day
1.5.1 | Research any DLC that would be required | Dylan | 1 day
1.6 | Research ways to distribute survey | Douglas | 2 days
1.7 | Research NAIT IT policies | Douglas | 1 day
1.8 | Research NAIT food policies | Douglas | 1 day
1.9 | Research volunteer recruitment channels | Karen | 1 day
1.9.1 | Research volunteer roles required | Karen | 1 day
1.1 | Research NAIT security policies | Kevin | 1 day
1.11 | Research prizes | Kevin | 1 day
1.12 | Compile costs | Kevin | 1 day | confirm total costs
| Research LAN Party complete |  | 0 days
2.0 | Plan LAN Party | Dylan | 34 days
2.1 | Create volunteer roles | Dylan | 1 day | volunteers confirmed
2.1.1 | Create volunteer training manual | Dylan | 1 day
2.1.2 | Create a discord for volunteer communication | Dylan | 1 day
2.2 | Volunteer recruitment | Bora | 1 day | Try to hit goal of 12 volunteers
2.2.1 | Confirm volunteers and availability | Bora | 1 day
2.2.2 | Create volunteer schedule | Bora | 1 day
2.3 | Create a run of show schedule | Dylan | 1 day
2.3.1 | Print run of show schedule for event and post on discord and social media | Dylan | 1 day
2.4 | Create a safety plan | Douglas | 1 day
2.4.1 | Print safety plan | Douglas | 1 day
2.5 | Create a code of conduct | Douglas | 3 days
2.5.1 | Print code of conduct for event | Douglas | 1 day
2.5.2 | Post code of conduct on event page | Douglas | 1 day
2.6 | Create registration form | Karen | 2 days
2.6.1 | Create QR code for registration form for marketing material | Karen | 1 day
2.7 | Create food and beverage survey | Karen | 2 days
2.7.1 | Create QR code for beverage survey for marketing material | Karen | 1 day
2.8 | Create pre and post event stress survey | Karen | 1 day
2.9 | Create quest cards | Karen | 1 day
2.1 | Contact potential sponsors | Kevin | 6 days
2.10.1 | Create sponsor tracking log | Kevin | 1 day
2.10.2 | Get sponsor logos for marketing materials | Kevin | 1 day
2.11 | Create an incident report form | Dylan | 1 day
2.12 | Create a budget | Dylan | 1 day
2.12.1 | Determine amount for contingency fund | Dylan | 1 day | 10% of total budget
2.13 | Create social media account | Jawan | 1 day | ookslife, Instagram
2.14 | Create a risk mitigation plan | Jawan | 1 day
2.15 | Create a walkthrough checklist | Jawan | 1 day
| Plan LAN Party Complete |  | 0 days
3.0 | Venue | Douglas | 35 days
3.1 | Book Venue with NAIT | Douglas | 1 day
3.1.1 | Finalize venue booking | Douglas | 1 day
3.2 | Create layout plan for the event | Douglas | 1 day
3.2.1 | Verify power outlet locations | Douglas | 1 day
3.3 | Conduct pre-event walkthrough | Douglas | 1 day
3.3.1 | Go through walkthrough checklist | Douglas | 1 day
3.3.2 | Document any preexisting damage | Douglas | 1 day
3.4 | Conduct post event walkthrough | Douglas | 1 day
3.4.1 | Go through walkthrough checklist | Douglas | 1 day
| Venue Complete |  | 0 days
4.0 | Marketing | Bora | 35 days
4.1 | Create marketing assets | Bora | 1 day
4.1.1 | Create Posters | Bora | 1 day
4.1.1.1 | Print posters | Bora | 1 day | 20 posters
4.1.2 | Create graphics for social media and discord posts | Bora | 1 day
4.2 | Post marketing assets around NAIT, discord, and social media | Bora | 33 days
4.2.1 | Launch registration form | Bora | 1 day
4.2.2 | Weekly event reminders on discord and social media | Bora | 30 days
4.4 | Create event signage | Bora | 1 day
4.4.1 | Create station signage | Bora | 1 day
| Marketing Complete |  | 0 days
5.0 | Equipment | Kevin | 30 days
5.1 | Send out request for borrowing equipment on discord and social media | Kevin | 21 days | Need 6 consoles + 4 controllers per console and 6 TV’s
5.2 | Secure rentals for any missing consoles, peripherals, or tv's | Kevin | 1 day | Any missing consoles, controllers, and TVs
5.3 | Procure Equipment | Kevin | 6 days
5.3.1 | Procure switches | Douglas | 6 days
5.3.2 | Procure HDMI and Ethernet cables | Douglas | 6 days
5.3.3 | Procure gaffers tape | Douglas | 6 days
5.3.4 | Procure games | Douglas | 6 days
5.3.4.1 | Procure any DLC that is required | Douglas | 6 days
5.3.5 | Procure cable mats | Kevin | 6 days
5.3.6 | Procure extension cables | Kevin | 6 days
5.3.7 | Procure power bars | Kevin | 6 days
5.3.8 | Procure volunteer lanyards | Kevin | 6 days
5.3.9 | Procure hand sanitizer and disinfectant wipes | Kevin | 6 days
5.4 | Create equipment inventory sheet | Kevin | 1 day
5.5 | Label all equipment and cables | Kevin | 1 day
5.5.1 | Ensure all borrowed equipment has contact information | Kevin | 1 day | logged in excel
5.6 | Procure Prizes | Dylan | 1 day
5.7 | Procure food and beverage | Karen | 1 day
5.8 | Pre event tech test | Jawan | 1 day
5.8.1 | Power load test | Bora | 1 day
5.8.2 | Network connectivity test | Bora | 1 day
| Equipment Complete |  | 0 days
6.0 | Hosting LAN Party | Group 6 | 2 days
6.1 | Load in equipment | Bora | 1 hr
6.2 | Physical setup | Douglas | 5 hrs
6.2.1 | Setup furniture | Douglas | 2 hrs
6.2.2 | Setup gaming stations | Kevin | 1 hr
6.2.3 | Cable management | Kevin | 1 hr
6.2.4 | Setup food and beverage table | Kevin | 0.5 hrs
6.2.5 | Final equipment and network test | Kevin | 1 hr
6.3 | Assign volunteers their roles | Dylan | 2 hrs
6.3.1 | Have safety meeting with volunteers | Dylan | 0.5 hrs
6.3.2 | Train volunteers | Dylan | 1.5 hrs
6.4 | Manage check in | Karen | 5 hrs
6.4.1 | Hand out quest cards | Karen | 5 hrs
6.4.1.1 | Take completed quest cards | Karen | 5 hrs
6.4.2 | Remind guests about pre-event survey | Karen | 5 hrs
6.5 | Create event incident reports as needed | Jawan | 9 hrs | incident report doc shared with everyone
6.6 | Prize draw | Jawan | 0.5 hrs
6.7 | Post event survey | Karen | 1 hr
6.8 | Event teardown | Kevin | 4 hrs
6.8.1 | Return borrowed equipment | Kevin | 1 day
6.8.2 | Return rented equipment | Kevin | 1 day
| Hosting LAN Party Complete |  | 0 day
7.0 | Post Event | Karen | 8 days
7.1 | Budget reconciliation | Karen | 3 days
7.1.1 | Collect all receipts | Karen | 1 day
7.1.2 | Update budget spreadsheet | Karen | 1 day | Enter actual cost vs planned
7.1.3 | Calculate final total + Remaining funds | Karen | 1 day
7.2 | Survey & Feedback analysis | Karen | 5 days
7.2.1 | Monitor Survey Responses | Karen | 5 days
7.2.2 | Send email reminder for survey | Karen | 4 days
7.2.3 | Summarize key metrics | Karen | 4 days | attendance feedback, enjoyment ratings etc.
7.3 | Final Closeout | Karen | 1 day
7.3.1 | Publish/ Share event highlights (photos, recap) | Karen | 1 day
7.3.2 | Send thank you notes to stakeholders | Karen | 1 day
7.4 | Analyze event incident reports | Dylan | 1 day
7.5 | Create event report | Jawan | 8 days
7.5.1 | Compile Event statistics | Jawan | 1 day
7.5.2 | Add photos and media highlights | Jawan | 1 day
7.5.3 | Finalize PDF event report | Jawan | 1 day | share with stake holders
| Post Event Complete |  | 0 days